## Slide 1
Executive Project
Dashboard
ReDefiners LMS Custom Frontend - Status Report
ReDefiners Education | March 2026 | v1.0

## Slide 2
Project Status Overview
ReDefiners LMS | Confidential
Overall Status
ON TRACK
Sprint
Sprint 12/12
Completion
100%
Budget
On Budget
Milestone | Target | Actual | Status
HTML Theme | Dec 2025 | Dec 2025 | Complete
React SPA | Feb 2026 | Feb 2026 | Complete
Deployment | Mar 2026 | Mar 2026 | Complete
Documentation | Mar 2026 | Mar 2026 | Complete

## Slide 3
Key Deliverables
ReDefiners LMS | Confidential
Deliverable | Target | Actual | Delta
Static HTML Pages | 230+ | 243 | +13
React Page Components | 160+ | 161 | +1
API Service Modules | 20+ | 24 | +4
Verification Screenshots | 200+ | 320 | +120
Documentation Files | 30+ | 35 | +5
Login Variants | 5 | 5 | 0
Theme Variants | 3 | 3 | 0
Seeded Demo Users | 20+ | 34 | +14

## Slide 4
Performance Metrics
ReDefiners LMS | Confidential
TTFB
176ms
Target: < 300ms
GOOD
FCP
567ms
Target: < 1500ms
GOOD
CLS
0.000
Target: < 0.1
GOOD
Bundle
64.9KB
Target: < 100KB
GOOD
All Core Web Vitals rated GOOD - measured via Chrome DevTools Protocol

## Slide 5
Security Posture
ReDefiners LMS | Confidential
Category | Found | Fixed | Remaining
Critical | 5 | 4 | 1
High | 6 | 5 | 1
Medium | 10 | 8 | 2
Low | 10 | 7 | 3
Total | 31 | 24 | 7
77% of findings remediated. All critical items addressed. Remaining items are low-severity UI hardening.

## Slide 6
Next Steps & Roadmap
ReDefiners LMS | Confidential
Initiative | Priority | Timeline | Owner
WCAG 2.1 AA Compliance | P1 | Q2 2026 | Dev
Playwright E2E Tests | P1 | Q2 2026 | QA
CDN Integration | P2 | Q2 2026 | DevOps
Sentry Error Monitoring | P1 | Q2 2026 | DevOps
PWA / Service Worker | P2 | Q2 2026 | Dev
WebSocket Notifications | P2 | Q3 2026 | Dev
Mobile App (React Native) | P3 | Q3-Q4 2026 | Dev
Multi-language (i18n) | P2 | Q3 2026 | Dev