## Feature Roadmap
Feature | Priority | Status | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Owner | Dependencies
Static HTML Theme (243 pages) | P0 | Done | BUILD |  |  |  |  | Dev | None
React SPA Scaffold | P0 | Done | BUILD |  |  |  |  | Dev | HTML Theme
Core Pages (Dashboard, Courses, Assignments) | P0 | Done |  | BUILD |  |  |  | Dev | SPA Scaffold
Canvas API Integration (24 modules) | P0 | Done |  | BUILD |  |  |  | Dev | SPA Scaffold
Authentication & CSRF | P0 | Done |  | BUILD |  |  |  | Dev | API Client
Theme System (3 themes + dark mode) | P1 | Done |  | BUILD |  |  |  | Dev | Core Pages
Login Page Variants (5 designs) | P2 | Done |  | BUILD |  |  |  | Dev | Auth
Admin Pages (45 components) | P1 | Done |  | BUILD |  |  |  | Dev | Auth + RBAC
Docker Deployment | P0 | Done |  | BUILD |  |  |  | DevOps | All code
CI/CD Pipeline | P1 | Done |  | BUILD |  |  |  | DevOps | Deployment
Security Audit & Fixes | P0 | Done |  | BUILD |  |  |  | Dev | All code
Performance Optimization | P1 | Done |  | BUILD |  |  |  | Dev | Deployment
Demo Data Seeding | P1 | Done |  | BUILD |  |  |  | Dev | Deployment
Documentation Suite (35 docs) | P1 | Done |  | BUILD |  |  |  | Dev/PM | All
WCAG 2.1 AA Compliance (Phase 1) | P1 | Planned |  |  | BUILD |  |  | Dev | Accessibility Report
Playwright E2E Tests | P1 | Planned |  |  | BUILD |  |  | QA | Test Plan
CDN Integration (CloudFlare) | P2 | Planned |  |  | BUILD |  |  | DevOps | DNS Access
Service Worker / PWA | P2 | Planned |  |  | BUILD |  |  | Dev | Performance
Sentry Error Monitoring | P1 | Planned |  |  | BUILD |  |  | DevOps | Deployment
Real-time Notifications (WebSocket) | P2 | Planned |  |  |  | BUILD |  | Dev | ActionCable
Student Mobile App (React Native) | P3 | Planned |  |  |  | BUILD | BUILD | Dev | API Client
Multi-language Support (i18n) | P2 | Planned |  |  |  | BUILD |  | Dev | All Pages
Advanced Analytics Dashboard | P2 | Planned |  |  |  | BUILD |  | Dev | Analytics API
LTI 1.3 Tool Configuration UI | P3 | Planned |  |  |  |  | BUILD | Dev | Canvas LTI
Content Import/Export Wizard | P2 | Planned |  |  |  | BUILD |  | Dev | Migrations API
Staging Environment | P1 | Planned |  |  | BUILD |  |  | DevOps | VPS Budget
Automated Backup Cron | P1 | Planned |  |  | BUILD |  |  | DevOps | DR Plan