## RACI Matrix
Activity | Project Sponsor | PM | Dev Lead | Developer | DevOps | QA | IT Admin | Faculty Rep
Project Initiation & Charter | A | R | C |  |  |  | I | I
Requirements Gathering | A | R | C |  |  |  | C | C
Architecture Design | I | C | R | C | C |  | I
UI/UX Design | A | C | R | R |  |  | I | C
Frontend Development (React) | I | C | A | R
Canvas API Integration | I |  | A | R
Theme System Implementation | I | C | A | R |  |  |  | C
Unit Testing |  |  | A | R |  | C
Visual Regression Testing |  | I | C | R |  | A
Performance Testing |  | I | R | C | C | A
Security Audit | I | I | R | C | C | A
Docker Deployment Setup | I | C | C |  | R | I | A
CI/CD Pipeline |  | C | C | C | R | I | A
SSL & Domain Setup |  |  | I |  | R |  | A
Demo Data Seeding |  | I | A | R |  |  |  | C
Documentation | I | R | A | C | C | C
User Training | I | R | C |  |  |  | C | A
UAT Coordination | A | R | C | C |  | A | C | C
Production Go-Live | A | R | C | C | R |  | A | I
Post-Launch Monitoring | I | I | C | C | R |  | A
Incident Response | I | I | A | R | R |  | C
Backup & Recovery |  | I | C |  | R |  | A
Change Management | A | R | C |  |  |  | C | C
Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed