## Risk Register
Risk ID | Category | Risk Description | Probability | Impact | Score | Mitigation Strategy | Owner | Status | Last Review
RSK-001 | Technical | Canvas API breaking changes in major version updates | Medium | High | 12 | Pin Canvas version, monitor release notes, maintain integration test suite | Dev Lead | Active | Mar 2026
RSK-002 | Technical | Session cookie expiry causes silent auth failures | Medium | Medium | 9 | Auto-detect 401 responses, redirect to login, show toast notification | Dev Lead | Mitigated | Mar 2026
RSK-003 | Security | XSS vulnerability in user-generated content | Low | High | 8 | DOMPurify sanitization on all HTML rendering, CSP headers | Dev Lead | Mitigated | Mar 2026
RSK-004 | Security | CSRF attack on state-changing API endpoints | Low | High | 8 | Canvas CSRF token extraction and injection on all non-GET requests | Dev Lead | Mitigated | Mar 2026
RSK-005 | Infrastructure | VPS resource exhaustion under peak load | Low | High | 8 | Docker memory limits, Redis LRU eviction, monitoring alerts | DevOps | Active | Mar 2026
RSK-006 | Infrastructure | SSL certificate renewal failure | Medium | Medium | 9 | Certbot auto-renewal every 12 hours, monitoring of cert expiry | DevOps | Active | Mar 2026
RSK-007 | Operational | Single point of failure (one VPS) | Medium | High | 12 | Document full recovery procedure, maintain offline backups, test quarterly | DevOps | Accepted | Mar 2026
RSK-008 | Operational | Database corruption or data loss | Low | Critical | 10 | Daily pg_dump backups, 4-week retention, tested restore procedure | DevOps | Active | Mar 2026
RSK-009 | Technical | Large file upload failures (> 100MB) | Medium | Low | 6 | Chunked upload with progress, retry logic, clear error messages | Dev Lead | Active | Mar 2026
RSK-010 | Technical | Theme CSS conflicts across browsers | Medium | Low | 6 | CSS custom properties, cross-browser testing, fallback values | Dev Lead | Mitigated | Mar 2026
RSK-011 | Business | Low user adoption of new UI | Medium | Medium | 9 | Phased rollout, training program, legacy access during transition | PM | Active | Mar 2026
RSK-012 | Business | Scope creep from feature requests | High | Medium | 12 | Strict batch delivery, documented PRD, change control process | PM | Active | Mar 2026
RSK-013 | Compliance | FERPA violation through data leakage | Very Low | Critical | 5 | No client-side data storage, audit logging, HTTPS only | Dev Lead | Mitigated | Mar 2026
RSK-014 | Technical | Dependency vulnerability (npm packages) | Medium | Medium | 9 | Weekly npm audit, Dependabot alerts, pin major versions | Dev Lead | Active | Mar 2026
RSK-015 | Infrastructure | DDoS attack on public-facing server | Low | High | 8 | Rate limiting via Nginx, CloudFlare CDN (recommended) | DevOps | Active | Mar 2026
RSK-016 | Operational | Knowledge loss if developer leaves | Medium | High | 12 | Comprehensive documentation (35+ docs), onboarding guide, CI/CD automation | PM | Mitigated | Mar 2026
RSK-017 | Technical | Browser compatibility issues | Low | Medium | 6 | Target Chrome/Firefox/Safari 100+, Vite modern build targets | Dev Lead | Active | Mar 2026
RSK-018 | Infrastructure | DNS propagation delays | Low | Medium | 6 | Low TTL on DNS records, direct IP access as fallback | DevOps | Active | Mar 2026